## PREINSPECTION
Lid up Pre-Inspection |  | Date: | 2024-01-17 |  | Done by: | Peter Hall-Patch, Riley Sykes, Maico Dalla Valle
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Pre-Inspection
Check for Lubrication leaks - motors, gearbox, jack screw | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - motor to gearbox | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - gearbox to screw | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - screw to synchro | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - couplings | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - motors | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - gearboxes | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - jack screws | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - yoke | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check limit switches - fasteners, alignment, togglability (check with Ops before toggle) | Y | [8 empty] | N
Check wiring to motor - when spares have been put in or originals replaced, after service | Y | Y |  |  | N |  | N
Check wiring to synchros - When elevating system is powered up
Check synchros for damage - when elevating system is powered up
Check on top of cylotron lid - no equipment that would interfere with lid up
Ensure crane is in "parked" position - station 12 | [11 empty] | Y
Pre-lift Synchro | 64 | 58 | 66 | 54 | 29 | 64 | 65 | 67 | 98 | 38 | 63
Notes:
Station 4: gearbox L - silicone needed to prevent leakage Station 5: L and R - check/swap seals Station 6: gearbox L minor leak front, gearbox R minor leak rear Station 8: too much grease in shaft

## LID UP
Lid up Operation |  | Date: |  |  | Time Lift Started: |  |  |  | Master Synchro. Pre
| Height Confirmation |  |  |  | Time Lift Ended: |  |  |  | Master Synchro. Post
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Pre-lift Synchro
During Lift
Jogging
Jog 1
Jog 2
Jog 3
Jog 4
Jog 5
Inspection During Lift
@3" check tank seal
Heat Check - After running for 20 minutes
Left Highfield
Motor
Right Highfield
Post-lift Synchro
Notes

## LID DOWN
Lid Down Operation |  | Date: |  |  | Time Started: |  |  |  | Master Synchro. Pre
[5 empty] | Time Completed: |  |  |  | Master Synchro. Post
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Synchro Before
Jogging
Jogging 1
Jogging 2
Jogging 3
Check During Operation
Left Highfield
Motor
Right Highfield
Post Lid-Down Synchro
Notes