## PREINSPECTION
Lid up Pre-Inspection |  | Date: | 2024-01-17 |  | Done by: | Peter Hall-Patch, Riley Sykes, Maico Dalla Valle
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Pre-Inspection
Check for Lubrication leaks - motors, gearbox, jack screw | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - motor to gearbox | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - gearbox to screw | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check coupling alignment - screw to synchro | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - couplings | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - motors | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - gearboxes | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - jack screws | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check fasteners - yoke | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check limit switches - fasteners, alignment, togglability (check with Ops before toggle) | Y | [8 empty] | Y
Check wiring to motor - when spares have been put in or originals replaced, after service | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check wiring to synchros - When elevating system is powered up | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check synchros for damage - when elevating system is powered up | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Check on top of cylotron lid - no equipment that would interfere with lid up | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Ensure crane is in "parked" position - station 12 | [11 empty] | Y
Pre-lift Synchro | 64 | 58 | 66 | 54 | 29 | 64 | 65 | 67 | 98 | 38 | 63 | 99921
Notes:
Station 4: gearbox L - silicone needed to prevent leakage Station 5: L and R - check/swap seals Station 6: gearbox L minor leak front, gearbox R minor leak rear Station 8: too much grease in shaft
Note on M21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Jogged to 55

## LID UP
Lid up Operation |  | Date: | 2021-01-28 |  | Time Lift Started: |  | 11:15 |  | Master Synchro. Pre |  | 2
| Height Confirmation |  | 46.5" |  | Time Lift Ended: |  | 11:57 |  | Master Synchro. Post |  | 47397
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Pre-lift Synchro
During Lift
Jogging
Jog 1 | [11 empty] | Jogged up once
Jog 2
Jog 3
Inspection During Lift
Temperature of Station 12
@3" check tank seal | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
Heat Check - After running for 20 minutes
Left Highfield
Motor | 36.8 | 40.4 | 38.2 | 31.8 | 32.4 | 30 | 35.7 | 32.5 | 31.6 | 30.3 | 42.5 | 39.2
Right Highfield
Post-lift Synchro | 47374 | 47377 | 47367 | 47366 | 47335 | 47377 | 47371 | 47373 | 47413 | 47337 | 47370 | 47364
Notes | Stations 2, 11, and 12 ran warmer than the others.

## LID DOWN
Lid Down Operation |  | Date: | 2025-03-21 |  | Time Started: |  | 9:56 |  | Master Synchro. Pre |  | 47428
[5 empty] | Time Completed: |  | 10:23 |  | Master Synchro. Post |  | 56
Station | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Synchro Before | 47374 | 47377 | 47367 | 47366 | 47335 | 47377 | 47371 | 47373 | 47413 | 47337 | 47370 | 47364
Jogging
Jogging 1
Jogging 2
Jogging 3
Check During Operation
Left Highfield
Motor | 31.3 | 33.4 | 28.9 | 36.5 | 33.3 | 32 | 30.7 | 33.6 | 36.8 | 36.4 | 36.6 | 39
Right Highfield
Post Lid-Down Synchro | 59 | 55 | 62 | 53 | 24 | 57 | 58 | 67 | 94 | 34 | 58 | 54
Notes | Smooth operation - no stoppage/jogging.