## Sheet1
Target Schedule 130(APR-SEP 2016) as of 2016-03-15
Color Codes---------- |  | Maintenance | New Target to SHC | SHC Available | Beam Off | Online Module |  | Conditioning | Shut Down/Mini Shut Down | Maint If Required | Stat Holiday | Development | Module Cool Down
Date |  | BL2A Off | Target Hall Activities | SHC | TCS | ITE | ITW | NOTE | Facility | Exp.# | Target Station | Target | Source
Apr-14 | Thursday | Winter Shut Down | Blocks Transfer / Storage to ITW |  |  | TM4 | TM2
Apr-15 | Friday | Winter Shut Down |  |  |  | TM4 | TM2
Apr-16 | Saturday | Winter Shut Down |  |  |  | TM4 | TM2
Apr-17 | Sunday | Winter Shut Down |  |  |  | TM4 | TM2
Apr-18 | Monday | Winter Shut Down |  |  |  | TM4 | TM2
Apr-19 | Tuesday |  |  |  |  | TM4 | TM2 |  |  | Start-up | ITW | Lp Ucx | TRILIS
Apr-20 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield | Start-up/ Yield | ITW | Lp Ucx | TRILIS
Apr-21 | Thursday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | Lp Ucx | TRILIS
Apr-22 | Friday |  |  |  |  | TM4 | TM2 |  | Yield/TITAN | S841/ Set up | ITW | Lp Ucx | TRILIS
Apr-23 | Saturday |  |  |  |  | TM4 | TM2 |  | TITAN | S1578 | ITW | Lp Ucx | TRILIS
Apr-24 | Sunday |  |  |  |  | TM4 | TM2 |  | TITAN | S1578 | ITW | Lp Ucx | TRILIS
Apr-25 | Monday |  |  |  |  | TM4 | TM2 |  | TITAN | S1578 | ITW | Lp Ucx | TRILIS
Apr-26 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  | Implantation | S841 | ITW | Lp Ucx | TRILIS
Apr-27 | Wednesday |  |  |  |  | TM4 | TM2 |  | Implantation | S841/Set up | ITW | Lp Ucx | TRILIS
Apr-28 | Thursday |  |  |  |  | TM4 | TM2 |  | Implantation | L112 | ITW | Lp Ucx | TRILIS
Apr-29 | Friday |  |  |  |  | TM4 | TM2 |  | Francium Trap | Set up/ S1218 | ITW | Lp Ucx | TRILIS
Apr-30 | Saturday |  |  |  |  | TM4 | TM2 |  | Francium Trap | S1218 | ITW | Lp Ucx | TRILIS
May-01 | Sunday |  |  |  |  | TM4 | TM2 |  | Implantation | L112 | ITW | Lp Ucx | TRILIS
May-02 | Monday |  |  |  |  | TM4 | TM2 |  | Implantation | L112 | ITW | Lp Ucx | TRILIS
May-03 | Tuesday | Maintenance |  |  |  | TM4 | TM2 |  |  | L112 | ITW | Lp Ucx | TRILIS
May-04 | Wednesday |  |  |  |  | TM4 | TM2 |  | Implantation | L112/Test | ITW | Lp Ucx | TRILIS
May-05 | Thursday |  |  |  |  | TM4 | TM2 |  | Implantation | Test | ITW | Lp Ucx | TRILIS
May-06 | Friday |  | Blocks Transfer/ ITW to ITE |  |  | TM4 | TM2 | Beam off Morning |  | Start-up | ITE | LpTa | TRILIS
May-07 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | Start-up/Yield | ITE | LpTa | TRILIS
May-08 | Sunday |  |  |  |  | TM4 | TM2 |  | BNMR | Set up/ TBA | ITE | LpTa | TRILIS
May-09 | Monday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-10 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-11 | Wednesday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-12 | Thursday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-13 | Friday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-14 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITE | LpTa | TRILIS
May-15 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITE | LpTa | TRILIS
May-16 | Monday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITE | LpTa | TRILIS
May-17 | Tuesday | Maint If Required | TM2 Move / ITW to SHC |  |  | TM4 |  | HpTa Target to SHC | Yield | S841 | ITE | LpTa | TRILIS
May-18 | Wednesday |  | TM2 Move / SHC to TCS |  | TM2 | TM4 |  |  | Yield | S841 | ITE | LpTa | TRILIS
May-19 | Thursday |  | Spent Target /SHC to Vault |  | TM2 | TM4 |  |  | Yield | S841 | ITE | LpTa | TRILIS
May-20 | Friday |  |  |  | TM2 | TM4 |  |  | TIGRESS | Set up | ITE | LpTa | TRILIS
May-21 | Saturday |  |  |  | TM2 | TM4 |  |  | TIGRESS | S1545 | ITE | LpTa | TRILIS
May-22 | Sunday |  |  |  | TM2 | TM4 |  |  | TIGRESS | S1545 | ITE | LpTa | TRILIS
May-23 | Monday | Victoria Day |  |  | TM2 | TM4 |  |  | TIGRESS/BNMR | S1545/Set up | ITE | LpTa | TRILIS
May-24 | Tuesday |  |  |  | TM2 | TM4 |  |  | BNMR | TBA | ITE | LpTa | TRILIS
May-25 | Wednesday | Maintenance | TM2 Move/ TCS to ITW |  |  | TM4 | TM2 |  |  |  | ITE | LpTa | TRILIS
May-26 | Thursday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-27 | Friday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITE | LpTa | TRILIS
May-28 | Saturday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA/Test | ITE | LpTa | TRILIS
May-29 | Sunday |  |  |  |  | TM4 | TM2 |  | N/A | Test | ITE | LpTa | TRILIS
May-30 | Monday |  | Blocks Transfer/ ITE to ITW |  |  | TM4 | TM2 | Beam off Morning | N/A | Start-up | ITW | HpTa | TRILIS
May-31 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  |  | Start-up | ITW | HpTa | TRILIS
Jun-01 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield | Yield/S841 | ITW | HpTa | TRILIS
Jun-02 | Thursday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-03 | Friday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-04 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-05 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-06 | Monday |  |  |  |  | TM4 | TM2 |  | BNMR | Set up/TBA | ITW | HpTa | TRILIS
Jun-07 | Tuesday | Maint If Required | TM4 MOVE/ITW to SHC/SHC to TCS |  | TM4 |  | TM2 | LpUCx Target to SHC | BNMR | TBA | ITW | HpTa | TRILIS
Jun-08 | Wednesday |  |  |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-09 | Thursday |  | Spent Target /SHC to Vault |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-10 | Friday |  |  |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-11 | Saturday |  |  |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-12 | Sunday |  |  |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-13 | Monday |  |  |  | TM4 |  | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-14 | Tuesday | Maintenance | TM4 Move/ TCS to ITE |  |  | TM4 | TM2 |  |  |  | ITW | HpTa | TRILIS
Jun-15 | Wednesday | Maintenance-Morning Only |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-16 | Thursday |  |  |  |  | TM4 | TM2 |  | BNMR | TBA | ITW | HpTa | TRILIS
Jun-17 | Friday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-18 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-19 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-20 | Monday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-21 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-22 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-23 | Thursday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-24 | Friday |  |  |  |  | TM4 | TM2 |  | Yield | S841 | ITW | HpTa | TRILIS
Jun-25 | Saturday |  |  |  |  | TM4 | TM2 |  | N/A | Test | ITW | HpTa | TRILIS
Jun-26 | Sunday |  |  |  |  | TM4 | TM2 |  | N/A | Test | ITW | HpTa | TRILIS
Jun-27 | Monday |  | Blocks Transfer/ ITW to ITE |  |  | TM4 | TM2 | Beam off Morning |  | Start-up | ITE | Lp UCx | IGLIS
Jun-28 | Tuesday | Maint If Required |  |  |  | TM4 | TM2 |  | Yield | Start-up/Yield | ITE | Lp UCx | IGLIS
Jun-29 | Wednesday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | Setup/S1457 | ITE | Lp UCx | IGLIS
Jun-30 | Thursday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1457 | ITE | Lp UCx | IGLIS
Jul-01 | Friday | Canada Day |  |  |  | TM4 | TM2 |  | TITAN | Set up/S1466 | ITE | Lp UCx | IGLIS
Jul-02 | Saturday |  |  |  |  | TM4 | TM2 |  | TITAN | S1466 | ITE | Lp UCx | IGLIS
Jul-03 | Sunday |  |  |  |  | TM4 | TM2 |  | TITAN | S1466 | ITE | Lp UCx | IGLIS
Jul-04 | Monday |  |  |  |  | TM4 | TM2 |  | TITAN | S1466 | ITE | Lp UCx | IGLIS
Jul-05 | Tuesday | Maintenance | TM2 Move / ITW to SHC |  |  | TM4 |  | HpSiC Target to SHC | TITAN | S1466 | ITE | Lp UCx | IGLIS
Jul-06 | Wednesday |  | TM2 Move / SHC to TCS |  | TM2 | TM4 |  |  | Yield | S841 | ITE | Lp UCx | IGLIS
Jul-07 | Thursday |  | Spent Target /SHC to Vault |  | TM2 | TM4 |  |  | Yield/TITAN | S841/Set up | ITE | Lp UCx | IGLIS
Jul-08 | Friday |  |  |  | TM2 | TM4 |  |  | TITAN | S1502 | ITE | Lp UCx | IGLIS
Jul-09 | Saturday |  |  |  | TM2 | TM4 |  |  | TITAN | S1502 | ITE | Lp UCx | IGLIS
Jul-10 | Sunday |  |  |  | TM2 | TM4 |  |  | TITAN | S1502 | ITE | Lp UCx | IGLIS
Jul-11 | Monday |  |  |  | TM2 | TM4 |  |  | TITAN | S1502 | ITE | Lp UCx | IGLIS
Jul-12 | Tuesday | Beam Development | TM2 Move / TCS to ITW |  |  | TM4 | TM2 |  | GRIFFIN | Set up | ITE | Lp UCx | IGLIS
Jul-13 | Wednesday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1519 | ITE | Lp UCx | IGLIS
Jul-14 | Thursday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1519 | ITE | Lp UCx | IGLIS
Jul-15 | Friday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1519 | ITE | Lp UCx | IGLIS
Jul-16 | Saturday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1519 | ITE | Lp UCx | IGLIS
Jul-17 | Sunday |  |  |  |  | TM4 | TM2 |  | N/A | Test | ITE | Lp UCx | IGLIS
Jul-18 | Monday |  | Blocks Transfer/ ITE to ITW |  |  | TM4 | TM2 | Beam off Morning | N/A | Start-up | ITW | HpSiC | TRILIS
Jul-19 | Tuesday | Maint If Required |  |  |  | TM4 | TM2 |  | N/A | Start-up | ITW | HpSiC | TRILIS
Jul-20 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield/TIGRESS | Yield/Set up | ITW | HpSiC | TRILIS
Jul-21 | Thursday |  |  |  |  | TM4 | TM2 |  | TIGRESS | Set up/S1646 | ITW | HpSiC | TRILIS
Jul-22 | Friday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1646 | ITW | HpSiC | TRILIS
Jul-23 | Saturday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1646 | ITW | HpSiC | TRILIS
Jul-24 | Sunday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1646 | ITW | HpSiC | TRILIS
Jul-25 | Monday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1646 | ITW | HpSiC | TRILIS
Jul-26 | Tuesday | Maintenance |  |  |  | TM4 | TM2 |  | TIGRESS | S1646 | ITW | HpSiC | TRILIS
Jul-27 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSiC | TRILIS
Jul-28 | Thursday |  |  |  |  | TM4 | TM2 |  | Yield/TUDA I | Yield/Set up | ITW | HpSiC | TRILIS
Jul-29 | Friday |  |  |  |  | TM4 | TM2 |  | TUDA I | S1381 | ITW | HpSiC | TRILIS
Jul-30 | Saturday |  |  |  |  | TM4 | TM2 |  | TUDA I | S1381 | ITW | HpSiC | TRILIS
Jul-31 | Sunday |  |  |  |  | TM4 | TM2 |  | TUDA I | S1381 | ITW | HpSiC | TRILIS
Aug-01 | Monday | BC Day |  |  |  | TM4 | TM2 |  | TUDA I | S1381 | ITW | HpSiC | TRILIS
Aug-02 | Tuesday | Beam Development | TM4 Move / ITE to SHC |  |  |  | TM2 | LpUCx Target to SHC | TUDA I | S1381 | ITW | HpSiC | TRILIS
Aug-03 | Wednesday |  | TM4 move / SHC to TCS |  | TM4 |  | TM2 |  | TUDA I/Yield | S1381/Yield | ITW | HpSiC | TRILIS
Aug-04 | Thursday |  | Spent Target /SHC to Vault |  | TM4 |  | TM2 |  | IRIS | Set up | ITW | HpSiC | TRILIS
Aug-05 | Friday |  |  |  | TM4 |  | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-06 | Saturday |  |  |  | TM4 |  | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-07 | Sunday |  |  |  | TM4 |  | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-08 | Monday |  |  |  | TM4 |  | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-09 | Tuesday | Maint If Required | TM4 Move / TCS to ITE |  |  | TM4 | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-10 | Wednesday |  |  |  |  | TM4 | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-11 | Thursday |  |  |  |  | TM4 | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-12 | Friday |  |  |  |  | TM4 | TM2 |  | IRIS | S1483 | ITW | HpSiC | TRILIS
Aug-13 | Saturday |  |  |  |  | TM4 | TM2 |  | IRIS | S1483/test | ITW | HpSiC | TRILIS
Aug-14 | Sunday |  |  |  |  | TM4 | TM2 |  | N/A | Test | ITW | HpSiC | TRILIS
Aug-15 | Monday |  | Blocks Transfer/ ITW to ITE |  |  | TM4 | TM2 | Beam off Morning | N/A | Start-up | ITE | Lp UCx | TRILIS
Aug-16 | Tuesday | Maintenance |  |  |  | TM4 | TM2 |  | N/A | Start -up | ITE | Lp UCx | TRILIS
Aug-17 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield/Implantation | Yield/L122 | ITE | Lp UCx | TRILIS
Aug-18 | Thursday |  |  |  |  | TM4 | TM2 |  | Implantation/GRIFFIN | L122/Set up | ITE | Lp UCx | TRILIS
Aug-19 | Friday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1468 | ITE | Lp UCx | TRILIS
Aug-20 | Saturday |  |  |  |  | TM4 | TM2 |  | GRIFFIN | S1468 | ITE | Lp UCx | TRILIS
Aug-21 | Sunday |  |  |  |  | TM4 | TM2 |  | GRIFFIN/Francium Trap | S1468/Set up | ITE | Lp UCx | TRILIS
Aug-22 | Monday |  |  |  |  | TM4 | TM2 |  | Francium Trap | S1218 | ITE | Lp UCx | TRILIS
Aug-23 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  | Francium Trap | S1218 | ITE | Lp UCx | TRILIS
Aug-24 | Wednesday |  |  |  |  | TM4 | TM2 |  | Francium Trap | S1218 | ITE | Lp UCx | TRILIS
Aug-25 | Thursday |  |  |  |  | TM4 | TM2 |  | Francium Trap/TRINAT | S1218/Set up | ITE | Lp UCx | TRILIS
Aug-26 | Friday |  |  |  |  | TM4 | TM2 |  | TRINAT | S1446 | ITE | Lp UCx | TRILIS
Aug-27 | Saturday |  |  |  |  | TM4 | TM2 |  | TIGRESS | Set up | ITE | Lp UCx | TRILIS
Aug-28 | Sunday |  |  |  |  | TM4 | TM2 |  | TIGRESS | Set up/S1481 | ITE | Lp UCx | TRILIS
Aug-29 | Monday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1481 | ITE | Lp UCx | TRILIS
Aug-30 | Tuesday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1481 | ITE | Lp UCx | TRILIS
Aug-31 | Wednesday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1481 | ITE | Lp UCx | TRILIS
Sep-01 | Thursday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1481 | ITE | Lp UCx | TRILIS
Sep-02 | Friday |  |  |  |  | TM4 | TM2 |  | TIGRESS | S1481 | ITE | Lp UCx | TRILIS
Sep-03 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | S481 | ITE | Lp UCx | TRILIS
Sep-04 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | Test | ITE | Lp UCx | TRILIS
Sep-05 | Monday | Labor day |  |  |  | TM4 | TM2 |  | N/A | Test | ITE | Lp UCx
Sep-06 | Tuesday | Mini Shut Down | TM2 Move / ITW to SHC |  |  | TM4 |  | New Target to SHC
Sep-07 | Wednesday | Mini Shut Down | TM2 Move / SHC to TCS |  | TM2 | TM4
Sep-08 | Thursday | Mini Shut Down | Spent Target /SHC to Vault |  | TM2 | TM4
Sep-09 | Friday | Mini Shut Down |  |  | TM2 | TM4
Sep-10 | Saturday | Mini Shut Down |  |  | TM2 | TM4