## Sheet1
Target Schedule 131(Sep-Dec 2017) as of 2016-09-02
Color Codes---------- |  | Maintenance | New Target to SHC | SHC Available | Beam Off | Online Module |  | Conditioning | Shut Down/Mini Shut Down | Maint If Required | Stat Holiday | Development | Module Cool Down
Date |  | BL2A Off | Target Hall Activities | SHC | TCS | ITE | ITW | NOTE | Exp.# | Facility | Target Station | Target | Source
Sep-06 | Tuesday | Maintenance | Blocks Transfer / ITE to ITW |  |  | TM4 | TM2 |  | Start-up |  | ITW | HpTa | TRILIS
Sep-07 | Wednesday |  |  |  |  | TM4 | TM2 |  | Start-up |  | ITW | HpTa | TRILIS
Sep-08 | Thursday |  |  |  |  | TM4 | TM2 |  | Yield / Test | Yield /GRIFFIN | ITW | HpTa | TRILIS
Sep-09 | Friday |  |  |  |  | TM4 | TM2 |  | Test / Set up | GRIFFIN /NMR | ITW | HpTa | TRILIS
Sep-10 | Saturday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-11 | Sunday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-12 | Monday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-13 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  |  | NMR | ITW | HpTa | TRILIS
Sep-14 | Wednesday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-15 | Thursday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-16 | Friday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-17 | Saturday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-18 | Sunday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-19 | Monday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-20 | Tuesday | Maint If Required | TM4 Move/ITE to SHC |  |  |  | TM2 | LpSiC Target to SHC | Test | NMR | ITW | HpTa | TRILIS
Sep-21 | Wednesday |  | TM4 Move/ SHC to TCS |  | TM4 |  | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-22 | Thursday |  | Spent Target Move/SHC to Vault |  | TM4 |  | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-23 | Friday |  |  |  | TM4 |  | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-24 | Saturday |  |  |  | TM4 |  | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-25 | Sunday |  |  |  | TM4 |  | TM2 |  | Test | NMR | ITW | HpTa | TRILIS
Sep-26 | Monday |  |  |  | TM4 |  | TM2 |  | Test | N/A | ITW | HpTa | TRILIS
Sep-27 | Tuesday | Mini Shut Down | TM4 Move/TCS to ITE |  |  | TM4 | TM2
Sep-28 | Wednesday | Mini Shut Down |  |  |  | TM4 | TM2
Sep-29 | Thursday | Mini Shut Down |  |  |  | TM4 | TM2
Sep-30 | Friday | Mini Shut Down |  |  |  | TM4 | TM2
Oct-01 | Saturday | Mini Shut Down |  |  |  | TM4 | TM2
Oct-02 | Sunday | Mini Shut Down |  |  |  | TM4 | TM2
Oct-03 | Monday | Mini Shut Down |  |  |  | TM4 | TM2
Oct-04 | Tuesday | Mini Shut Down | Blocks Transfer / ITW to ITE |  |  | TM4 | TM2 |  | Start-up | N/A
Oct-05 | Wednesday |  |  |  |  | TM4 | TM2 |  | Start-up / Yield | Yield | ITE | LpTa | IGLIS
Oct-06 | Thursday |  |  |  |  | TM4 | TM2 |  | Start-up / Yield | Yield | ITE | LpTa | IGLIS
Oct-07 | Friday |  |  |  |  | TM4 | TM2 |  | Set up | TIGRESS | ITE | LpTa | IGLIS
Oct-08 | Saturday |  |  |  |  | TM4 | TM2 |  | S1624 | TIGRESS | ITE | LpTa | IGLIS
Oct-09 | Sunday |  |  |  |  | TM4 | TM2 |  | S1624 | TIGRESS | ITE | LpTa | IGLIS
Oct-10 | Monday | Thanksgiving |  |  |  | TM4 | TM2 |  | S1624 | TIGRESS | ITE | LpTa | IGLIS
Oct-11 | Tuesday | Beam Development | TM2 Move / ITW to SHC |  |  | TM4 |  | HpSiC Target to SHC | S1624 | TIGRESS | ITE | LpTa | IGLIS
Oct-12 | Wednesday |  | TM2 Move / SHC to TCS |  | TM2 | TM4 |  |  | Set up / S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-13 | Thursday |  | Spent Target Move/SHC to Vault |  | TM2 | TM4 |  |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-14 | Friday |  |  |  | TM2 | TM4 |  |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-15 | Saturday |  |  |  | TM2 | TM4 |  |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-16 | Sunday |  |  |  | TM2 | TM4 |  |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-17 | Monday |  |  |  |  | TM4 | TM2 |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-18 | Tuesday | Maint If Required | TM2 Move / TCS to ITW |  |  | TM4 | TM2 |  | S1601 | GRIFFIN | ITE | LpTa | IGLIS
Oct-19 | Wednesday |  |  |  |  | TM4 | TM2 |  | Set up | TIGRESS | ITE | LpTa | IGLIS
Oct-20 | Thursday |  |  |  |  | TM4 | TM2 |  | S1480 | TIGRESS | ITE | LpTa | IGLIS
Oct-21 | Friday |  |  |  |  | TM4 | TM2 |  | S1480 | TIGRESS | ITE | LpTa | IGLIS
Oct-22 | Saturday |  |  |  |  | TM4 | TM2 |  | S1480 | TIGRESS | ITE | LpTa | IGLIS
Oct-23 | Sunday |  |  |  |  | TM4 | TM2 |  | S1480 | TIGRESS | ITE | LpTa | IGLIS
Oct-24 | Monday |  |  |  |  | TM4 | TM2 |  | S1480 | TIGRESS | ITE | LpTa | IGLIS
Oct-25 | Tuesday | Maintenance | Blocks Transfer / ITE to ITW |  |  | TM4 | TM2 |  | Start-up | N/A | ITW | HpSic | FEBIAD
Oct-26 | Wednesday |  |  |  |  | TM4 | TM2 |  | Start-up | N/A | ITW | HpSic | FEBIAD
Oct-27 | Thursday |  |  |  |  | TM4 | TM2 |  | Start-up / Yield | Yield | ITW | HpSic | FEBIAD
Oct-28 | Friday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Oct-29 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Oct-30 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Oct-31 | Monday |  |  |  |  | TM4 | TM2 |  | Yield / Set up | IRIS | ITW | HpSic | FEBIAD
Nov-01 | Tuesday | Beam Development | TM4 Move / ITE to SHC |  |  | TM4 | TM2 | Hp Ta Target to SHC | Set up | IRIS | ITW | HpSic | FEBIAD
Nov-02 | Wednesday |  | TM4 Move / SHC to TCS |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-03 | Thursday |  | Spent Target Move/SHC to Vault |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-04 | Friday |  |  |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-05 | Saturday |  |  |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-06 | Sunday |  |  |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-07 | Monday |  |  |  | TM4 |  | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-08 | Tuesday | Maint If Required | TM4 Move/ TCS to ITE |  |  | TM4 | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-09 | Wednesday |  |  |  |  | TM4 | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-10 | Thursday |  |  |  |  | TM4 | TM2 |  | S1537 | IRIS | ITW | HpSic | FEBIAD
Nov-11 | Friday | Remembrance Day |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Nov-12 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Nov-13 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITW | HpSic | FEBIAD
Nov-14 | Monday |  |  |  |  | TM4 | TM2 |  | Test | N/A | ITW | HpSic | FEBIAD
Nov-15 | Tuesday | Maintenance | Blocks Transfer / ITW to ITE |  |  | TM4 | TM2 |  |  |  | ITE | HpTa | TRILIS
Nov-16 | Wednesday |  |  |  |  | TM4 | TM2 |  | Start-up | N/A | ITE | HpTa | TRILIS
Nov-17 | Thursday |  |  |  |  | TM4 | TM2 |  | Start-up /Yield | Yield | ITE | HpTa | TRILIS
Nov-18 | Friday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITE | HpTa | TRILIS
Nov-19 | Saturday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITE | HpTa | TRILIS
Nov-20 | Sunday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITE | HpTa | TRILIS
Nov-21 | Monday |  |  |  |  | TM4 | TM2 |  | Yield | Yield | ITE | HpTa | TRILIS
Nov-22 | Tuesday | Beam Development | TM2 Move /ITW to SHC to TCS |  |  | TM4 |  | LpUCx Target to SHC | Yield | Yield/OSAKA | ITE | HpTa | TRILIS
Nov-23 | Wednesday |  | Spent Target /SHC to Vault |  | TM2 | TM4 |  |  | Set up / S1183 | OSAKA | ITE | HpTa | TRILIS
Nov-24 | Thursday |  |  |  | TM2 | TM4 |  |  | S1183 | OSAKA | ITE | HpTa | TRILIS
Nov-25 | Friday |  |  |  | TM2 | TM4 |  |  | S1183 | OSAKA | ITE | HpTa | TRILIS
Nov-26 | Saturday |  |  |  | TM2 | TM4 |  |  | S1183 | OSAKA | ITE | HpTa | TRILIS
Nov-27 | Sunday |  |  |  | TM2 | TM4 |  |  | S1183 | OSAKA | ITE | HpTa | TRILIS
Nov-28 | Monday |  |  |  | TM2 | TM4 |  |  | S1183 /set up | NMR | ITE | HpTa | TRILIS
Nov-29 | Tuesday | Maint If Required | TM2 Move / TCS to ITW |  |  | TM4 | TM2 |  | Test | NMR | ITE | HpTa | TRILIS
Nov-30 | Wednesday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITE | HpTa | TRILIS
Dec-01 | Thursday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITE | HpTa | TRILIS
Dec-02 | Friday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITE | HpTa | TRILIS
Dec-03 | Saturday |  |  |  |  | TM4 | TM2 |  | Test | NMR | ITE | HpTa | TRILIS
Dec-04 | Sunday |  |  |  |  | TM4 | TM2 |  | Test | N/A | ITE | HpTa | TRILIS
Dec-05 | Monday |  |  |  |  | TM4 | TM2 |  | Start-up | N/A | ITE | HpTa | TRILIS
Dec-06 | Tuesday | Maintenance | Blocks Transfer / ITE to ITW |  |  | TM4 | TM2 |  | Start-up | N/A | ITW | Lp UCx | TRILIS
Dec-07 | Wednesday |  |  |  |  | TM4 | TM2 |  | Yield /Set up | Yield/Polarizer | ITW | Lp UCx | TRILIS
Dec-08 | Thursday |  |  |  |  | TM4 | TM2 |  | S1329 | Polarizer | ITW | Lp UCx | TRILIS
Dec-09 | Friday |  |  |  |  | TM4 | TM2 |  | S1329 | Polarizer | ITW | Lp UCx | TRILIS
Dec-10 | Saturday |  |  |  |  | TM4 | TM2 |  | S1329 | Polarizer | ITW | Lp UCx | TRILIS
Dec-11 | Sunday |  |  |  |  | TM4 | TM2 |  | S1329 | Polarizer | ITW | Lp UCx | TRILIS
Dec-12 | Monday |  |  |  |  | TM4 | TM2 |  | Set up /L122 | Implantation | ITW | Lp UCx | TRILIS
Dec-13 | Tuesday | Beam Development |  |  |  | TM4 | TM2 |  | L122 | Implantation | ITW | Lp UCx | TRILIS
Dec-14 | Wednesday |  |  |  |  | TM4 | TM2 |  | L122 | Implantation | ITW | Lp UCx | TRILIS
Dec-15 | Thursday |  |  |  |  | TM4 | TM2 |  | Set up / M1424 | NMR | ITW | Lp UCx | TRILIS
Dec-16 | Friday |  |  |  |  | TM4 | TM2 |  | M1424 | NMR | ITW | Lp UCx | TRILIS
Dec-17 | Saturday |  |  |  |  | TM4 | TM2 |  | M1424 | NMR | ITW | Lp UCx | TRILIS
Dec-18 | Sunday |  |  |  |  | TM4 | TM2 |  | M1424 | NMR | ITW | Lp UCx | TRILIS
Dec-19 | Monday |  |  |  |  | TM4 | TM2 |  | M1424 | NMR | ITW | Lp UCx | TRILIS
Dec-20 | Tuesday | Maint If Required |  |  |  | TM4 | TM2 |  | Test | N/A | ITW | Lp UCx | TRILIS
Dec-21 | Wednesday | Shut Down |  |  |  | TM4 | TM2
Dec-22 | Thursday | Shut Down |  |  |  | TM4 | TM2
Dec-23 | Friday | Shut Down |  |  |  | TM4 | TM2
Dec-24 | Saturday | Shut Down |  |  |  | TM4 | TM2
Dec-25 | Sunday | Shut Down |  |  |  | TM4 | TM2
Dec-26 | Monday | Shut Down |  |  |  | TM4 | TM2
Dec-27 | Tuesday | Shut Down |  |  |  | TM4 | TM2
Dec-28 | Wednesday | Shut Down |  |  |  | TM4 | TM2
Dec-29 | Thursday | Shut Down |  |  |  | TM4 | TM2
Dec-30 | Friday | Shut Down |  |  |  | TM4 | TM2
Dec-31 | Saturday | Shut Down |  |  |  | TM4 | TM2